## Sheet1
Proposed
Task	Sub Task		Effort (days)
Analysis/design			7
	current and future architecture	2
	messaging reqs and architecture	5
Docker fundamentals			5
	CentOS
	Azul Java (ease change to Oracle Java)
	build scripts
	docker secrets
	testing
Logging			8
	mP bootstrap logging
	logging from running container
	Tomcat logging
	testing
CI/CD setup			10
	Q/A, automated testing setup
	testing
Repository configuration			5
	MariaDB (external)
	DB JDBC drivers
	potentially others
	testing
Shib integration			10
	Either Shib+Spring security
	or Apache+Shib running in the same container
Upgrades			5
	Detect, announce, point to documentation
Documentation			2
Add-ons			5
	TIER beacon
	Multi-process container

		Sum	57

Optional
Docker compose			30
	for LDAP/AD & possibly other typical systems
	keystores mng (ssl connectivity)
	other typical topics
		Sum	30

		Total	87

Assumption
Automated builds and Q/A setup in TIER infrastructure.
	Legal issues related to packaging, for example Java, MySQL/MariaDB GPL JDBC driver

Out-of-scope
midPoint will be shipped as one application, no separation of frontend and backend packaging
Messaging, inbound and outbound implementation is out of scope for now, we will focus on requirements and architecture only.
No JMX/SNMP monitoring, nor modern metrics systems in this SoW. Just the Beacon
Shipping more system drivers/connectors (Cloud, REST, MS Exchange, Banner …) with containers - for now a vision, not in scope, targeted for different SoW
We are not covering all items in the SoW proposal as stated here:
	https://spaces.internet2.edu/display/TPWG/TIER+midPoint+-+Docker+Reference+Implementation
	Some items are out-of-scope, like messaging, LDAP only as optional package