## Internet2 Todos 2019-08-01T08_11_36-0500
Issue Type	Sub-Type	Issue key	Epic	Issue	Summary	Status	Start Date	Due Date
Story		TAP-56	(de-)Prov. Tools	21222	GitHub Repo with Markdown	In Progress	2019-08-01	2019-08-15
Story		TAP-75	Id Match	26598	Draft OAI 3 specification of ID Match API	Open	2019-08-04	2019-08-15
Story	One-time Task	TAP-47	Id Match	25784	Update status with Warren, Scott Koranda and BennO	In Progress	2019-08-09	2019-08-20
Story	One-time Task	TAP-51	Msg Bus	21991	Invite Carl Waldbieser and Michael Hodges onto a call on messaging patterns; UMDCP is headed to messaging approaches, too.	Open	2019-08-26	2019-08-30
Story		TAP-27	Com-mP integ.	25562	Mapping SOR user info to midPoint via push	In Progress	2019-01-01	2019-08-31
Story		TAP-10	Grouper-mP	25245	Filtering and Paging to browse Grouper	In Progress	2019-08-07	2019-09-07
Story		TAP-9	MP-Grouper	25244	Generic loader for generic groups	In Progress	2019-08-01	2019-09-08
Story		TAP-12	Grouper-mP	25247	Map groups to midPoint role objects	In Progress	2019-05-15	2019-09-15
Story		TAP-52	(de-)Prov. Tools	21990	Containers for midPoint with layers for various connectors	In Progress	2019-07-15	2019-09-21
Epic		TAP-55	Schema def	20802	Schema definition and extension mechanisms and practices	To Do	2019-01-01	2019-10-30
Story		TAP-62	Schema def	21513	Recipe for Schema Extensions at local campuses	Open	2019-08-01	2019-10-30
Epic		TAP-61	Non-Person Entities	21514	Non-person entities and their schema;	To Do	2019-09-07	2019-11-15
Epic		TAP-58	Tools, Best Pract.	20807	Tools, connectors, best practices, examples	To Do	2019-01-01	2019-11-30
Story		TAP-50	Msg Bus	21992	Introduce Security Event Token work for next generation ideas on using JWTs to carry security and IAM event messages	Open	2019-10-15	2019-11-30
Story		TAP-79	Banner as SoR	26702	Design a Banner Ethos connector	In Progress	2019-07-24	2019-12-07
Epic		TAP-46	Id Match	25783	Implement Standalone ID Match Service	To Do	2019-10-01	2019-12-07
Epic		TAP-63	Client/Svc Registry	20806	Simple client/service registry	To Do	2019-12-01	2019-12-31
Epic		TAP-49	Instrument APIs	17776	Instrument Component APIs to Report Operation Invocation Events" Published	To Do	2019-11-01	2020-02-01
Story		TAP-69	Grouper-mP	26582	Async task handler to support Live Sync	Done
Story		TAP-71	Grouper-mP	26584	Evaluate Demo(s)	Done
Story		TAP-73	Grouper-mP	26586	Full-Sync	Done